## Voting System Database ad441990
Name | Assign | Status | Created Time | Priority | Deadline | Comments
Create voters module | Kevorn | In Progress | October 7, 2021 | High | October 8, 2021 | Complete seeder. models and migrations by deadline
Create election module | Shaneika | In Progress | October 7, 2021 | High | October 8, 2021 | Complete seeder. models and migrations by deadline
Create ballots module | Latoya | In Progress | October 7, 2021 | High | October 8, 2021 | Complete seeder. models and migrations by deadline. Completed
Create ballot questions module | Shaneika | In Progress | October 7, 2021 | Medium | October 9, 2021 | Complete seeder. models and migrations by deadline
Create ballot voters module | Virgo | In Progress | October 7, 2021 | Medium | October 9, 2021 | Complete seeder. models and migrations by deadline
Create ballot answers module | Kevorn | In Progress | October 7, 2021 | Medium | October 9, 2021 | Complete seeder. models and migrations by deadline
Create ballot messages module | Latoya | In Progress | October 7, 2021 | Medium | October 9, 2021 | Complete seeder. models and migrations by deadline completed
Modify users module and authentication | Richard | Completed | October 7, 2021 | High | October 8, 2021 | Update seeder. models and migrations by deadline
Integrate dashboard template into app | Richard | Completed | October 7, 2021 | Medium | October 9, 2021
Integrate twillio api | Richard | In Progress | October 7, 2021 | Medium | October 9, 2021
Integrate oauth api | Virgo | New | October 7, 2021 | Low | October 10, 2021
Create question option module | Latoya | In Progress | October 8, 2021 | Medium |  | Mainly create, migrations.